## Sheet1
ID | As a... | I want to be able to.. | So that... | Priority | Sprint | Status
1 | User | play any mp3 file from hard-disk drive | I can listen to any audio file of mp3 format | 1 | 1 | In progress
2 | User | play, pause or stop music at any time | I don't have to wait till the music ends | 1 | 2 | To be started
3 | User | control music volume | I can adjust the sound according to my preference | 1 | 2 | To be started
4 | User | select multiple audio files | I can create playlist | 1 | 3 | To be started
5 | User | see song name, artist's name, track length of the song currently playing | I can know all the details about the song | 2 | 3 | To be started
6 | User | shuffle/repeat songs | I can listen to songs in random order everytime | 2 | 4 | To be started
7 | User | create music library | I can find & sort songs by title/artist/genre/album | 2 | 3 | To be started
8 | User | mark songs as favorite | I can have a list of favorite songs to listen without having to search them again | 2 | 3 | To be started
9 | User | switch between previous and next song | I can change my current song if I don't want to hear it | 2 | 4 | To be started
10 | User | control playback speed | I can increse or decrese speed of the audio file while playing | 3 | 5 | To be started