## Sheet1
ID | User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | As a user, I want to be able to play,pause,stop music at my time so that I don't have to wait till the music ends | Design graphical user interface for play,pause,stop button | Day 1: 3
|  | Write code for the interface of play,pause,stop button | Day 2: 2; Day 3: 1
|  | Write code for enabling play,pause,stop button | Day 4: 3
Test buttons & audio file play,pause,stop events | bar: Day 5 to Day 7
2 | As a user, I want to control music volume so that I can adjust the sound according to my preference | Design graphical user interface for volume button | Day 1: 3
|  | Write code for controling volume from the desktop application | Day 2: 2; Day 3: 1
|  | Write code for controling volume from the keyboard | Day 4: 3; Day 5: 1
Test volume button from both desktop app & keyboard | bar: Day 6 to Day 7