## Sheet1
ID | User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | As a user, I want to be able to select multiple audio files so that I can create playlist | Write code for selecting multiple audio files from the desktop app | Day 1: 3
|  | Design "create playlist" interface | Day 2: 2
|  | Write code for the interface of new playlist & create playlist option | Day 3: 2
|  | Write code for showing saved playlists | Day 4: 3
Test create playlist related events | bar: Day 5 to Day 7
2 | As a user, I want to see song name, artist's name, track length of the song currently playing so that I can know all the details about the song | Design graphical user interface for showing song and artist name,track length of the song | Day 1: 3
|  | Write code for the interface for showing song and artist details | Day 2: 2; Day 3: 1
|  | Write code for fetching song and artist details | Day 4: 3; Day 5: 1
Test song and artist details for the various songs | bar: Day 6 to Day 7